## Sheet1
Defect ID | Date Found | Module / Component | Defect Description | Severity | Steps to Reproduce | Root Cause | Resolution / Fix | Status
DEF-001 | 2026-02-12 | Frontend - CallerUI | DTMF Keypad vanishes after starting a call | High | 1. Navigate to CallerUI 2. Click 'Start Call' 3. Keypad disappears | UI visibility conditionally relied on callState === 'idle', hiding the main block. | Removed 'idle' condition wrapping the keypad and disabled invalid keys during calls. | Closed
DEF-002 | 2026-02-28 | Build System | Hook order transpilation errors (TS2448 / TS2454) | High | 1. Run npm run build 2. Observe use-before-declaration compiler errors | playBase64Audio and handleDtmfPress hooks relied on dependencies declared below them in code. | Reordered the React useCallback hooks sequentially to satisfy dependency mapping constraints. | Closed
DEF-003 | 2026-03-13 | Frontend - Keyboard | Global keyboard shortcuts trigger while typing in inputs | Medium | 1. Start call 2. Type in chat box 3. Type number '1' | The global keydown event listener wasn't ignoring editable DOM nodes. | Added tagName checks (INPUT, TEXTAREA) to the keyboard event listener to safely ignore typing. | Closed
DEF-004 | 2026-03-29 | Call Simulator | Empty Audio ArrayBuffer causes playback to hang | Medium | 1. Trigger DTMF 2. Backend sends emptyTTS 3. Next hooks fail | The Web Audio API fails to process a 0-length buffer and halts the queue. | Added an early exit if (totalLength === 0) playNext(); guard before array slicing. | Closed