## Product Backlog
Planned Sprint | Actual Sprint | US ID | Story Points | User Story Description | MoSCoW | Dependency (US ID) | Assignee | Status
Sprint 1 | Sprint 1 | US001 | 3 | As a researcher, I want to gather information about the traditional IVR System. | Must Have | — | Backend Team | Completed
Sprint 2 | Sprint 2 | US002 | 5 | As a Backend Developer, I want to make some Basic APIs for the traditional IVR System. | Must Have | US001 | Backend Team | Completed
Sprint 3 | Sprint 3 | US003 | 8 | As an AI developer, I want to integrate an AI layer in the traditional IVR System to make it an AI Conversational IVR System with the help of Machine Learning and NLU. | Must Have | US001, US002 | Backend Team | Completed
Sprint 3 | Sprint 3 | US003A | 8 | As an AI developer, I want to integrate NLU, STT, intent detection, entity extraction, Data Flow Diagram, and TTS into the system. | Must Have | US003 | Backend Team | Completed
Sprint 4 | Sprint 4 | US004 | 6 | As a frontend developer, I want to create an interactive User Interface for the users so that they can use and interact with the system efficiently without any issues. | Must Have | US003A | Frontend Team | Completed
Sprint 4 | Sprint 4 | US005 | 4 | As a DevOps engineer, I want to deploy and integrate the entire system in a test environment for demonstration. | Could Have | US003A, US004 | Both Teams | Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate (Hours) | Actual Effort (Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
SPRINT 1 BACKLOG
US001 | T1 | Gathered all the information of the Traditional IVR System | 06-Feb-2026 | 07-Feb-2026 | Doc Team 1 | Data Collection | Done | 6 | 6 | bar: Day 1 to Day 14
US001 | T2 | Documented all the information in a word file with proper architecture and use cases | 09-Feb-2026 | 10-Feb-2026 | Doc Team 2 | Data Collection | Done | 5 | 5 | bar: Day 2 to Day 4
US002 | T3 | Made some basic API endpoints for the traditional IVR System | 22-Feb-2026 | 28-Feb-2026 | Backend Team 1 | API Development | Done | 6 | 6 | bar: Day 1 to Day 14
US003 | T4 | Integrated the AI layer in the System | 03-Mar-2026 | 06-Mar-2026 | Backend Team 2 | AI Integration | Done | 10 | 10 | bar: Day 4 to Day 6
US003A | T5 | Implemented NLU, STT, intent detection in the system | 07-Mar-2026 | 11-Mar-2026 | Backend Team 3 | AI Integration | Done | 12 | 12 | bar: Day 1 to Day 14
US003A | T6 | Implemented entity extraction, data flow, TTS in the system | 12-Mar-2026 | 14-Mar-2026 | Backend Team 4 | AI Integration | Done | 5 | 5 | bar: Day 6 to Day 9
US004 | T7 | Implemented User Interface for the better experience | 18-Mar-2026 | 24-Mar-2026 | Frontend Team 1 | Web Dev | In Progress | 5 | — | bar: Day 1 to Day 14
US005 | T8 | Tested some edge cases and deployed the system | 25-Mar-2026 | 28-Mar-2026 | Both Teams | Deployment | Planned | 5 | — | bar: Day 11 to Day 13
TOTAL | [7 empty] | 54

## Stand up Meeting
Sprint | Day | Date | Yesterday's Work | Today's Plan | Impediments | Action Taken
Sprint 1 | Day 1 | 06-Feb-2026 | Project kickoff and planning | Gather IVR system information | None | Drafted the system design of the project
Sprint 2 | Day 2 | 09-Feb-2026 | Gathered IVR system information | Create base backend structure | None | Created base structure of the backend
Sprint 3 | Day 3 | 22-Feb-2026 | Set up backend structure | Create API endpoints | Integrating AI layer dependencies | Creating API endpoints
Sprint 4 | Day 4 | 03-Mar-2026 | Created API endpoints | Test and validate endpoints | Testing API endpoints | Testing and validating endpoints
Sprint 5 | Day 5 | 07-Mar-2026 | Validated API endpoints | Build base frontend UI | Improvement in the frontend UI | Created the base UI using JS
Sprint 6 | Day 6 | 10-Mar-2026 | Built base frontend UI | Improve and refine UI | Addition of security and stress testing | Improved the UI
Sprint 7 | Day 7 | 12-Mar-2026 | Refined UI | Integrate AI layer (STT/TTS) | Addition of AI layer | Stress tested and added security
Sprint 8 | Day 8 | 13-Mar-2026 | Integrated AI layer | Create STT and TTS modules | Entity tracking and endpoint checking | Created STT and TTS modules
Sprint 9 | Day 9 | 14-Mar-2026 | Created STT/TTS modules | Manage session management | Managing session management | Entity tracking and endpoint checking
Sprint 10 | Day 10 | 17-Mar-2026 | Worked on session management | Enable cloud-based database module | Testing session management and cloud DB migration | Added session management
Sprint 11 | Day 11 | 18-Mar-2026 | Enabled cloud-based DB module | Migrate to Supabase | Migrating to Supabase | Tested session management
Sprint 12 | Day 12 | 19-Mar-2026 | Migrated to Supabase | End-to-end testing of the project | Testing the project end to end | Migrated to Supabase
Sprint 13 | Day 13 | 24-Mar-2026 | Completed E2E testing | Deploy the project | Deployment of the project | Stress tested the entire project
Sprint 14 | Day 14 | 25-Mar-2026 | Deployed application | Post-deployment monitoring | None | Deployed the application in Vercel

## Retrospection
SL # | Sprint # | Sprint Start Date | Sprint End Date | Sprint Velocity (Story Points) | Team Member | Start Doing | Stop Doing | Continue Doing | Action Taken
1 | 1 | 06-Feb-2026 | 08-Feb-2026 | 3 | Varun Kumar | Drafting the system design of the application | Starting development without a documented system design | Extending AI Hospital IVR Web Simulator capabilities | Drafted the system design of the application
2 | 2 | 09-Feb-2026 | 21-Feb-2026 | 5 | Varun Kumar | Setting up proper backend architecture and folder structure | Jumping into coding without establishing base structure | Building and documenting the backend foundation | Created base structure of the backend
3 | 3 | 22-Feb-2026 | 02-Mar-2026 | 8 | Varun Kumar | Writing automated tests for each API endpoint before merging | Creating API endpoints without test coverage | REST API development and code reviews | Created API endpoints; Tested endpoints
4 | 4 | 03-Mar-2026 | 06-Mar-2026 | 8 | Varun Kumar | Adding request/response validation on all endpoints | Skipping input validation on existing API endpoints | REST API development and code reviews | Added input validation; Tested endpoints
5 | 5 | 07-Mar-2026 | 09-Mar-2026 | 6 | Varun Kumar | Implementing component-based and responsive UI architecture | Writing monolithic JavaScript for frontend without modularity | Iterative UI improvements based on user feedback | Created the base UI using JS
6 | 6 | 10-Mar-2026 | 11-Mar-2026 | 4 | Varun Kumar | Using reusable UI components to speed up development | Rewriting similar UI sections without reusable components | Iterative UI improvements based on user feedback | Improved the UI using reusable components
7 | 7 | 12-Mar-2026 | 12-Mar-2026 | 8 | Varun Kumar | Integrating AI layer (STT/TTS) with proper validation and fallback | Delaying security testing to the end of the sprint | Stress testing and security hardening across all modules | Added AI layer; Stress tested and added security
8 | 8 | 13-Mar-2026 | 13-Mar-2026 | 12 | Varun Kumar | Testing STT/TTS modules in isolation before full integration | Merging AI modules without unit-level testing | Stress testing and security hardening across all modules | Created STT and TTS modules; Unit tested AI modules
9 | 9 | 14-Mar-2026 | 14-Mar-2026 | 5 | Varun Kumar | Centralised cloud-based session management from the start | Using in-memory / stateless session tracking approach | Entity tracking and endpoint health monitoring | Entity tracking and endpoint checking; Added session management
10 | 10 | 17-Mar-2026 | 17-Mar-2026 | 5 | Varun Kumar | Enabling cloud-based database module early in the sprint | Deferring cloud database migration until last steps | Entity tracking and endpoint health monitoring | Added session management; Tested cloud DB module
11 | 11 | 18-Mar-2026 | 18-Mar-2026 | 4 | Varun Kumar | Adopting cloud-first database strategy using Supabase for all modules | Maintaining local/in-memory database implementations | Testing session management workflows post-migration | Tested session management; Migrated to Supabase
12 | 12 | 19-Mar-2026 | 23-Mar-2026 | 4 | Varun Kumar | Running regression tests immediately after each migration step | Migrating all data without incremental testing checkpoints | Testing session management workflows post-migration | Migrated to Supabase; End-to-end tested the project
13 | 13 | 24-Mar-2026 | 24-Mar-2026 | 8 | Varun Kumar | Setting up CI/CD pipeline for automated builds and deployments | Manual deployment processes and ad-hoc testing | End-to-end testing and full system stress testing | Stress tested the entire project; Initiated deployment
14 | 14 | 25-Mar-2026 | 28-Mar-2026 | 4 | Varun Kumar | Documenting deployment steps and post-deployment monitoring | Deploying without post-deployment health checks | End-to-end testing and full system stress testing | Deployed the application in Vercel; Post-deployment monitoring